## Summary
First dose administered | Second dose administered
217603 | 87297

## Cumulative Plan
Date | Cumulative vaccinations planned | Cumulative vaccinations model | Cumulative vaccinations administered | The information provided in the vaccinations planned column is based on DHB plans.
2021-02-21 | 0 |  | 163 | An earlier version of this report had slightly different figures for initial weeks.
2021-02-28 | 4491 |  | 6719 | These were estimates from the MoH formed at the beginning of the program and have been updated following consultation with DHBs on their plans.
2021-03-07 | 14420 |  | 15630
2021-03-14 | 21715 |  | 23168
2021-03-21 | 35595 |  | 36604
2021-03-28 | 56290 |  | 56300
2021-04-04 | 84595 |  | 84809
2021-04-11 | 117992 |  | 121303
2021-04-18 | 164107 |  | 170263
2021-04-25 | 216158 |  | 224321
2021-05-02 | 273749 |  | 281161
2021-05-09 | 338813 |  | 304900
2021-05-16 | 414824
2021-05-23 | 493606
2021-05-30 | 581932
2021-06-06 | 680290
2021-06-13 | 793013
2021-06-20 | 909422
2021-06-27 | 1033848
2021-07-04 | 1161952 | 1161952
2021-07-11 |  | 1369338
2021-07-18 |  | 1576724
2021-07-25 |  | 1750577
2021-08-01 |  | 2063064
2021-08-08 |  | 2375551
2021-08-15 |  | 2654505
2021-08-22 |  | 2932955
2021-08-29 |  | 3226921
2021-09-05 |  | 3520887
2021-09-12 |  | 3814853
2021-09-19 |  | 4348809
2021-09-26 |  | 4882765
2021-10-03 |  | 5416721
2021-10-10 |  | 5950677
2021-10-17 |  | 6484633
2021-10-24 |  | 7018589
2021-10-31 |  | 7552545
2021-11-07 |  | 7707286
2021-11-14 |  | 7862027
2021-11-21 |  | 8016768
2021-11-28 |  | 8016768
2021-12-05 |  | 8016768

## DHB Plan as at 14.04.2021
DHB Vaccination Plan
As at 14 April 2021
| Actual Vaccinations 21st Feb to 4th Apr 2021 (as at 13 April 2021) | Week ending | [12 empty] | Total Planned 5 April to 30 June 2021 | Total Actual plus Plan
DHB |  | 2021-04-11 | 2021-04-18 | 2021-04-25 | 2021-05-02 | 2021-05-09 | 2021-05-16 | 2021-05-23 | 2021-05-30 | 2021-06-06 | 2021-06-13 | 2021-06-20 | 2021-06-27 | 2021-07-04
Auckland Metro | 41641 | 15049 | 16900 | 19300 | 21750 | 26836 | 30222 | 33817 | 42031 | 45945 | 49975 | 51375 | 52475 | 50675 | 456350 | 497991
Bay of Plenty | 1545 | 462 | 804 | 1214 | 2088 | 2346 | 3018 | 2778 | 4530 | 5400 | 6594 | 6264 | 6204 | 6204 | 47906 | 49451
Canterbury | 5414 | 1465 | 3364 | 3759 | 3999 | 6399 | 6939 | 7927 | 9346 | 9898 | 10618 | 10618 | 10618 | 10618 | 95568 | 100982
Capital & Coast and Hutt Valley | 6988 | 4298 | 4728 | 4318 | 4298 | 3978 | 4008 | 7126 | 4599 | 4560 | 7299 | 4869 | 4056 | 7299 | 65436 | 72424
Hawke's Bay | 1217 | 553 | 989 | 700 | 3668 | 3268 | 4682 | 3128 | 3128 | 3128 | 3128 | 4128 | 4008 | 3688 | 38196 | 39413
Lakes | 1330 | 1400 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 3500 | 3500 | 3500 | 3990 | 4830 | 4830 | 35630 | 36960
MidCentral | 120 | 126 | 270 | 690 | 726 | 1163 | 1705 | 2437 | 2448 | 2580 | 3487 | 8075 | 7985 | 7940 | 39632 | 39752
Nelson Marlborough | 4789 | 1160 | 1800 | 2000 | 2100 | 2260 | 2305 | 2160 | 2235 | 2420 | 2400 | 2100 | 3050 | 3750 | 29740 | 34529
Northland | 1080 | 1627 | 4730 | 2575 | 4295 | 4000 | 3285 | 3170 | 2000 | 4100 | 3085 | 2350 | 4000 | 5000 | 44217 | 45297
South Canterbury | 1229 | 864 | 1080 | 1180 | 880 | 1275 | 925 | 600 | 675 | 1725 | 2050 | 2050 | 2000 | 2000 | 17304 | 18533
Southern | 3870 | 2224 | 2020 | 6400 | 3600 | 2880 | 8200 | 5400 | 5400 | 5400 | 7200 | 7200 | 7200 | 7200 | 70324 | 74194
Tairāwhiti | 620 |  | 585 | 500 | 534 | 1055 | 1100 | 534 | 470 | 600 | 1045 | 1100 | 1600 | 1600 | 10723 | 11343
Taranaki | 1268 | 329 | 400 | 300 | 600 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 8829 | 10097
Waikato | 5658 | 2100 | 3615 | 4015 | 4073 | 4649 | 4457 | 4275 | 4124 | 5142 | 6952 | 6840 | 10950 | 11850 | 73042 | 78700
Wairarapa | 0 | 120 | 390 | 600 | 900 | 975 | 975 | 1000 | 1000 | 1000 | 2250 | 2250 | 2250 | 2250 | 15960 | 15960
West Coast | 0 | 30 | 120 | 300 | 390 | 600 | 810 | 1050 | 1140 | 1260 | 1440 | 1500 | 1500 | 1500 | 11640 | 11640
Whanganui | 91 | 180 | 450 | 390 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 10020 | 10111
Other Sites | 7735 | 2021-04-11: 1410; 2021-04-18: 2190; 2021-04-25: 2130; 2021-05-02: 1110 | 6840 | 14575
Total | 84595 | 33397 | 46115 | 52051 | 57591 | 65064 | 76011 | 78782 | 88326 | 98358 | 112723 | 116409 | 124426 | 128104 | 1077357 | 1161952
The information provided in this table is based on DHB plans. We anticipate that there could be a potential variance of up to ten percent (plus or minus) in actual vaccination numbers. This is on the basis that, for example, an unplanned significant event could affect roll-out implementation or some DHBs might exceed their planned vaccination numbers. Actuals vary slightly from website due to an earlier date of extraction. Note a change to the table heading. The dates presented are actually the week ending dates, not the week commencing dates as previously stated.

## DHB Plan Variance
DHB Vaccination Plan
As at 5 May 2021
Week Ending
DHB |  | To 4 April | 2021-04-11 | 2021-04-18 | 2021-04-25 | 2021-05-02 | Cumulative
Auckland Metro | Plan | 41641 | 15049 | 16900 | 19300 | 21750 | 114640
Auckland Metro | Actual | 41724 | 15065 | 16429 | 17256 | 19448 | 109922
Auckland Metro | Variance | 83 | 16 | -471 | -2044 | -2302 | -4718
Bay of Plenty | Plan | 1545 | 462 | 804 | 1214 | 2088 | 6113
Bay of Plenty | Actual | 1545 | 837 | 1289 | 2031 | 2192 | 7894
Bay of Plenty | Variance | 0 | 375 | 485 | 817 | 104 | 1781
Canterbury | Plan | 5414 | 1465 | 3364 | 3759 | 3999 | 18001
Canterbury | Actual | 5417 | 1479 | 5451 | 5806 | 5261 | 23414
Canterbury | Variance | 3 | 14 | 2087 | 2047 | 1262 | 5413
Capital & Coast and Hutt Valley | Plan | 6988 | 4298 | 4728 | 4318 | 4298 | 24630
Capital & Coast and Hutt Valley | Actual | 7003 | 4428 | 4787 | 5071 | 5812 | 27101
Capital & Coast and Hutt Valley | Variance | 15 | 130 | 59 | 753 | 1514 | 2471
Hawke's Bay | Plan | 1217 | 553 | 989 | 700 | 3668 | 7127
Hawke's Bay | Actual | 1219 | 594 | 1253 | 1461 | 2128 | 6655
Hawke's Bay | Variance | 2 | 41 | 264 | 761 | -1540 | -472
Lakes | Plan | 1330 | 1400 | 1680 | 1680 | 1680 | 7770
Lakes | Actual | 1332 | 832 | 899 | 1583 | 1633 | 6279
Lakes | Variance | 2 | -568 | -781 | -97 | -47 | -1491
MidCentral | Plan | 120 | 126 | 270 | 690 | 726 | 1932
MidCentral | Actual | 120 | 177 | 366 | 995 | 1240 | 2898
MidCentral | Variance | 0 | 51 | 96 | 305 | 514 | 966
Nelson Marlborough | Plan | 4789 | 1160 | 1800 | 2000 | 2100 | 11849
Nelson Marlborough | Actual | 4829 | 2889 | 2418 | 3822 | 3381 | 17339
Nelson Marlborough | Variance | 40 | 1729 | 618 | 1822 | 1281 | 5490
Northland | Plan | 1080 | 1627 | 4730 | 2575 | 4295 | 14307
Northland | Actual | 1080 | 1699 | 1731 | 1743 | 3748 | 10001
Northland | Variance | 0 | 72 | -2999 | -832 | -547 | -4306
South Canterbury | Plan | 1229 | 864 | 1080 | 1180 | 880 | 5233
South Canterbury | Actual | 1229 | 547 | 680 | 1186 | 959 | 4601
South Canterbury | Variance | 0 | -317 | -400 | 6 | 79 | -632
Southern | Plan | 3870 | 2224 | 2020 | 6400 | 3600 | 18114
Southern | Actual | 3948 | 2790 | 5319 | 3948 | 3141 | 19146
Southern | Variance | 78 | 566 | 3299 | -2452 | -459 | 1032
Tairawhiti | Plan | 620 | 0 | 585 | 500 | 534 | 2239
Tairawhiti | Actual | 610 | 0 | 734 | 623 | 229 | 2196
Tairawhiti | Variance | -10 | 0 | 149 | 123 | -305 | -43
Taranaki | Plan | 1268 | 329 | 400 | 300 | 600 | 2897
Taranaki | Actual | 1267 | 330 | 418 | 450 | 600 | 3065
Taranaki | Variance | -1 | 1 | 18 | 150 | 0 | 168
Waikato | Plan | 5658 | 2100 | 3615 | 4015 | 4073 | 19461
Waikato | Actual | 5661 | 1930 | 2964 | 4232 | 4263 | 19050
Waikato | Variance | 3 | -170 | -651 | 217 | 190 | -411
Wairarapa | Plan | 0 | 120 | 390 | 600 | 900 | 2010
Wairarapa | Actual | 0 | 113 | 477 | 506 | 559 | 1655
Wairarapa | Variance | 0 | -7 | 87 | -94 | -341 | -355
West Coast | Plan | 0 | 30 | 120 | 300 | 390 | 840
West Coast | Actual | 0 | 34 | 127 | 308 | 398 | 867
West Coast | Variance | 0 | 4 | 7 | 8 | 8 | 27
Whanganui | Plan | 91 | 180 | 450 | 390 | 900 | 2011
Whanganui | Actual | 90 | 180 | 509 | 862 | 840 | 2481
Whanganui | Variance | -1 | 0 | 59 | 472 | -60 | 470
Other Sites | Plan | 7735 | 1410 | 2190 | 2130 | 1110 | 14575
Other Sites | Actual | 7735 | 2570 | 3109 | 2175 | 1008 | 16597
Other Sites | Variance | 0 | 1160 | 919 | 45 | -102 | 2022
Total | Plan | 84595 | 33397 | 46115 | 52051 | 57591 | 273749
Total | Actual | 84809 | 36494 | 48960 | 54058 | 56840 | 281161
Total | Variance | 214 | 3097 | 2845 | 2007 | -751 | 7412

## Date
Date | First dose administered | Second dose administered
2021-02-18 | 1 | 0
2021-02-19 | 29 | 0
2021-02-20 | 65 | 0
2021-02-21 | 68 | 0
2021-02-22 | 448 | 0
2021-02-23 | 358 | 0
2021-02-24 | 815 | 0
2021-02-25 | 1099 | 0
2021-02-26 | 1610 | 0
2021-02-27 | 1342 | 0
2021-02-28 | 884 | 0
2021-03-01 | 1411 | 0
2021-03-02 | 1492 | 0
2021-03-03 | 1983 | 0
2021-03-04 | 1632 | 0
2021-03-05 | 1278 | 0
2021-03-06 | 602 | 0
2021-03-07 | 513 | 0
2021-03-08 | 1072 | 0
2021-03-09 | 1425 | 0
2021-03-10 | 1314 | 0
2021-03-11 | 1336 | 0
2021-03-12 | 1044 | 2
2021-03-13 | 751 | 4
2021-03-14 | 578 | 12
2021-03-15 | 1617 | 265
2021-03-16 | 1929 | 233
2021-03-17 | 1645 | 364
2021-03-18 | 1593 | 470
2021-03-19 | 1691 | 771
2021-03-20 | 558 | 715
2021-03-21 | 941 | 644
2021-03-22 | 1053 | 1197
2021-03-23 | 1584 | 1107
2021-03-24 | 1971 | 1584
2021-03-25 | 1826 | 1531
2021-03-26 | 3367 | 1290
2021-03-27 | 1151 | 871
2021-03-28 | 681 | 483
2021-03-29 | 3798 | 1119
2021-03-30 | 4168 | 1499
2021-03-31 | 5437 | 1328
2021-04-01 | 5200 | 1244
2021-04-02 | 1722 | 295
2021-04-03 | 1412 | 335
2021-04-04 | 757 | 195
2021-04-05 | 923 | 291
2021-04-06 | 3518 | 1437
2021-04-07 | 5107 | 2143
2021-04-08 | 6460 | 1764
2021-04-09 | 5410 | 1928
2021-04-10 | 3266 | 690
2021-04-11 | 2476 | 1081
2021-04-12 | 5989 | 1722
2021-04-13 | 6776 | 1625
2021-04-14 | 6496 | 1517
2021-04-15 | 6780 | 1839
2021-04-16 | 6644 | 2603
2021-04-17 | 3787 | 1122
2021-04-18 | 1474 | 586
2021-04-19 | 5058 | 2037
2021-04-20 | 6039 | 2986
2021-04-21 | 6485 | 3423
2021-04-22 | 6120 | 3866
2021-04-23 | 7692 | 3545
2021-04-24 | 3058 | 1376
2021-04-25 | 1467 | 906
2021-04-26 | 1383 | 862
2021-04-27 | 6649 | 3202
2021-04-28 | 7194 | 3656
2021-04-29 | 7133 | 4956
2021-04-30 | 7881 | 5004
2021-05-01 | 3466 | 1940
2021-05-02 | 1600 | 1914
2021-05-03 | 6043 | 4461
2021-05-04 | 7978 | 5257

## DHBofService
DHB of service | First dose administered | Second dose administered
Auckland | 28364 | 12871
Bay of Plenty | 7221 | 1862
Canterbury | 21252 | 3973
Capital and Coast | 14334 | 6998
Counties Manukau | 40430 | 21534
Hawke's Bay | 6214 | 1584
Hutt Valley | 6013 | 2647
Lakes | 5047 | 1590
MidCentral | 3371 | 334
Nelson Marlborough | 12808 | 5775
Northland | 9087 | 1922
Other sites | 9204 | 7872
South Canterbury | 3772 | 1440
Southern | 16039 | 5113
Tairāwhiti | 1887 | 549
Taranaki | 2196 | 1121
Waikato | 15471 | 5117
Wairarapa | 1790 | 81
Waitematā | 9683 | 4577
West Coast | 929 | 60
Whanganui | 2491 | 277

## DHBofResidence
DHB of residence | First dose administered | Second dose administered
Auckland | 26595 | 13362
Bay of Plenty | 7600 | 2144
Canterbury | 22515 | 5080
Capital and Coast | 14323 | 7122
Counties Manukau | 29410 | 13664
Hawke's Bay | 6331 | 1710
Hutt Valley | 6505 | 3179
Lakes | 4841 | 1550
MidCentral | 6011 | 2372
Nelson Marlborough | 12953 | 5988
Northland | 9115 | 2125
Overseas / Unknown | 185 | 60
South Canterbury | 3792 | 1439
Southern | 16283 | 5339
Tairāwhiti | 1907 | 585
Taranaki | 2392 | 1223
Waikato | 15907 | 5469
Wairarapa | 1908 | 213
Waitematā | 25016 | 13901
West Coast | 927 | 87
Whanganui | 3087 | 685

## Ethnicity
Ethnic group | First dose administered | Second dose administered
Māori | 20081 | 7712
Pacific Peoples | 13890 | 6085
Asian | 41235 | 16775
European / Other | 140028 | 55544
Unknown | 2369 | 1181

## Gender
Gender | First dose administered | Second dose administered
Female | 138888 | 51328
Male | 78444 | 35859
Other / Unknown | 271 | 110

## Age
Ten Year Age Group | First dose administered | Second dose administered
10 to 19 | 3991 | 1570
20 to 29 | 37412 | 16986
30 to 39 | 39827 | 17497
40 to 49 | 36307 | 15605
50 to 59 | 45898 | 18628
60 to 69 | 34633 | 12627
70 to 79 | 12479 | 3560
80 to 89 | 5104 | 721
90 + years / Unknown | 1952 | 103